Migration Execution Plan

WordPress → Bricks: Step-by-Step Process

Samotics  |  February 2026

Total scope: ~65 items to actively migrate or build. ~80 items to redirect. The rest are already covered or can be dropped.

Estimated timeline: 6–8 weeks across 5 phases, assuming one person executing with AI assistance.

Dependency: Each phase builds on the previous. Blog infrastructure (Phase 3) requires Phase 2 templates. Industry pages (Phase 2) reference case studies from Phase 1.

# Execution Overview

Five phases, ordered by business impact and dependency. Each phase has concrete steps, owners, and deliverables.

| Phase | Focus | Duration | Key Deliverables |
| --- | --- | --- | --- |
| Phase 0 | Pre-Migration Setup | 2–3 days | Redirects, analytics baseline, blog infrastructure decisions |
| Phase 1 | Flagship Case Studies | 1 week | Top 6 customer stories rewritten into new template |
| Phase 2 | Missing Industry Pages + Remaining Case Studies | 1–2 weeks | Wastewater, cement, airports pages. 7 more case studies. |
| Phase 3 | Blog & Knowledge Base Migration | 2 weeks | ~20 SEO blog posts migrated with updated links and templates |
| Phase 4 | News, Legal, FAQs, Cleanup | 1 week | Partnership news, legal pages, FAQ consolidation, final redirects |

Phase 0   Pre-Migration Setup

Duration: 2–3 days

Get the foundations right before moving any content. This phase prevents broken links, lost SEO equity, and analytics blind spots.

Step 0.1: Export current analytics baseline  →  Owner: Marketing

- Pull Google Analytics data for the old site: top 50 pages by organic traffic, top 20 by conversions.

- Export Search Console data: top queries, click-through rates, indexed pages.

- Flag any old URLs with significant backlink profiles (use Ahrefs, Semrush, or similar).

- Document the top 10 referral sources driving traffic to old content.

✓ Deliverables: Analytics baseline spreadsheet · Backlink report

Step 0.2: Set up redirect map  →  Owner: Developer

- Create a CSV mapping every old URL to its new-site equivalent or a sensible fallback.

- Categories:

  - COVERED pages → map to exact new page (e.g. /products/sam4 → /sam4)

  - ARCHIVE pages → redirect to closest relevant new page (e.g. /lp/condition-monitoring-solution → /)

  - DROP pages → redirect to homepage or relevant parent

  - MERGE pages → redirect to the new page they merged into

- Implement as WordPress redirects (Redirection plugin or server-level 301s) so they work the moment the old site is replaced.

- Test every redirect before go-live. Broken redirects are the single biggest migration risk.

✓ Deliverables: Redirect CSV (old URL → new URL) · Redirect plugin configured

Step 0.3: Decide blog infrastructure  →  Owner: Marketing + Developer

- The new site needs a blog. Decide: Bricks template with WordPress native posts, or a separate blog subdomain?

- Recommendation: Use WordPress native posts with a Bricks archive template. Keeps everything in one CMS.

- Build the blog archive template in Bricks (list view, category filters, pagination).

- Build the blog single-post template in Bricks (consistent header/footer, CTA blocks, related posts).

- Set up categories: Blog, Case Studies, News, Knowledge Base, Webinars, Events.

✓ Deliverables: Blog archive template · Blog single-post template · Category structure

Step 0.4: Build case study template in Bricks  →  Owner: Developer

- The detection-story template already exists. Build a longer-form case study template for flagship stories.

- Template structure:

  - Hero: customer logo + headline result + industry tag

  - Context: 1–2 paragraphs on customer and their challenge

  - Solution: what SAM4 deployment looked like

  - Results: 3–4 metric cards (cost saved, downtime prevented, ROI, detection count)

  - Quote: customer stakeholder quote

  - Related: link to other detection stories from same customer

  - CTA: demo request

✓ Deliverables: Case study page template (HTML + CSS)

Phase 1   Flagship Case Studies

Duration: 1 week

Rewrite the six highest-value customer stories. These are the proof points that sales teams link to, prospects search for, and industry pages reference. Get these right first — everything else builds on them.

Step 1.1: Yorkshire Water: £390K saved  →  Owner: Content + Technical review

- Source: old site /case-studies/yorkshire-water-saved-390k (14K chars)

- Rewrite into new case study template. Lead with £390K saving and pollution prevention.

- Key content to extract:

  - 600+ pump stations monitored

  - Specific fault types detected (bearing degradation, blockages, belt failures)

  - £390K in avoided costs

  - Pollution events prevented

  - Digital Transformation Award win

- Cross-link to existing Yorkshire Water detection stories on new site.

- Get sign-off from customer success team on any quoted figures.

✓ Deliverables: Published case study page

Step 1.2: ArcelorMittal: 31 hours of downtime prevented  →  Owner: Content

- Source: old site /case-studies/arcelormittal-prevented-downtime (4.1K chars)

- Lead with 27 faults detected ahead of time, 31 hours saved.

- Steel vertical — link from metals-mining industry page.

- Keep it tight. The original is already concise.

✓ Deliverables: Published case study page

Step 1.3: Vitens: 7% operational efficiency increase  →  Owner: Content

- Source: old site /case-studies/vitens-increased-efficiency (12K chars)

- This is the strongest energy efficiency case study. Lead with 7% gain.

- Bridges health and energy monitoring — cross-link from water page and energy-efficiency page.

- Extract specific pump curve insights and efficiency metrics.

✓ Deliverables: Published case study page

Step 1.4: Schiphol Airport: improved baggage handling  →  Owner: Content

- Source: old site /case-studies/schiphol-baggage-handling (3K chars)

- Airport vertical proof point. Reference alongside Stansted.

- Short source material — may need to supplement with internal data.

✓ Deliverables: Published case study page

Step 1.5: Nyrstar: 800% ROI in 11 months  →  Owner: Content

- Source: old site /case-studies/nyrstar-800-roi (2.3K chars)

- The strongest financial proof point. 800% ROI headline carries weight.

- Metals/mining vertical — link from metals-mining industry page.

✓ Deliverables: Published case study page

Step 1.6: Southern Water: 3 failures caught, £748K saved  →  Owner: Content

- Source: old site /case-studies/southern-water-success (2.5K chars)

- UK water vertical. Pairs with Yorkshire Water for UK water dominance story.

- Check if Southern Water approves updated version.

✓ Deliverables: Published case study page

Phase 2   Missing Industry Pages + Remaining Case Studies

Duration: 1–2 weeks

Fill the gaps in industry coverage and migrate the second tier of case studies. After this phase, every active Samotics vertical has a dedicated page with supporting proof points.

Step 2.1: Build wastewater industry page  →  Owner: Content + Developer

- This is Samotics' strongest vertical. It deserves a dedicated page separate from the clean water page.

- Source: old site /industries/wastewater (129K chars — extract, don't copy)

- Page structure (follow water.html pattern):

  - Hero: wastewater-specific value proposition

  - Challenges: aging infrastructure, CSO compliance, energy costs, AMP8 context

  - How SAM4 helps: blockage detection, bearing failure, energy optimisation

  - Customer logos: Yorkshire Water, Southern Water, Anglian Water, Thames Water, United Utilities, NI Water

  - Featured case study: Yorkshire Water

  - Detection stories carousel

  - CTA

- Extract specific asset types: sewage pumps, inlet screws, RAS pumps, aeration blowers.

✓ Deliverables: wastewater.html + wastewater.css published

Step 2.2: Build cement industry page  →  Owner: Content + Developer

- Source: old site /industries/cement (14K chars)

- Decide: standalone cement page, or merge into metals-mining as a sub-section?

- If standalone: follow the chemicals.html pattern. If merged: add cement section to metals-mining page.

- Key assets in cement: kiln drive motors, raw mill drives, clinker cooler fans, conveyor drives.

✓ Deliverables: Cement page published (or merged section)

Step 2.3: Build airports industry page  →  Owner: Content + Developer

- Source: old site /industries/airports (12K chars)

- Two customer proof points: Schiphol and London Stansted.

- Key assets: baggage handling conveyor motors, HVAC systems, escalator drives.

- Niche but growing vertical. Build as a lightweight page.

✓ Deliverables: airports.html + airports.css published

Step 2.4: Decide on wind energy page  →  Owner: Marketing

- The old site has a small wind energy page (4.4K chars).

- Decision required: is wind energy still an active vertical for Samotics?

- If yes: build a lightweight page. If no: redirect to homepage and remove from navigation.

✓ Deliverables: Decision documented. Page built or redirect configured.

Step 2.5: Migrate remaining case studies  →  Owner: Content

- 7 case studies to rewrite into new template:

  - Stansted: improved baggage handling (2.8K chars) — airports vertical

  - Sabesp: submersible pump efficiency (2.9K chars) — international water

  - Belt-driven equipment prevention (7.1K chars) — cross-industry

  - Borehole pump prevention (7K chars) — water vertical

  - Inlet screw failure prevention (5.3K chars) — wastewater vertical

  - 9x faults in steel manufacturing (10.5K chars) — compilation, may work better as a blog post

  - Broken sine wave filter in ESPs (3.5K chars) — oil & gas vertical

- Use the case study template from Phase 0. Keep each rewrite under 1,000 words.

- Link each case study from its relevant industry page.

✓ Deliverables: 7 case study pages published

Step 2.6: Merge use-case pages into existing pages  →  Owner: Content

- The old site has 3 standalone use-case pages (stop downtime, reduce energy, prevent pollution).

- These shouldn't exist as standalone pages on the new site. The narrative is covered by the problem page and industry pages.

- Action:

  - Stop downtime (91K) → content already covered by problem.html. Set up 301 redirect.

  - Reduce energy (111K) → content covered by energy-efficiency.html. Extract any missing stats. Redirect.

  - Prevent pollution (73K) → pollution prevention is water-specific. Extract into water.html and new wastewater page. Redirect.

✓ Deliverables: 3 redirects configured. Any extracted content added to target pages.

Phase 3   Blog & Knowledge Base Migration

Duration: 2 weeks

Move the SEO-valuable blog content. These posts drive organic traffic and educate prospects. Don't rewrite them from scratch — update links, strip Elementor, and fit them into the new blog template.

Step 3.1: Migrate Tier 1 blog posts (highest traffic)  →  Owner: Content

- 5 posts with the highest likely organic traffic:

  - What is condition monitoring? (2025 guide) — 18.6K chars. Top-of-funnel keyword.

  - Guide to 5 major CM technologies — 20.6K chars. Comprehensive comparison.

  - Pump failure: causes, modes, prevention — 18.4K chars. Core SEO topic.

  - ESA explained (the right way) — 25.9K chars. Overlaps with ESA page; keep as blog, cross-link.

  - MCSA: what and how — 8.7K chars. Cross-link with ESA page.

- For each: strip Elementor markup, preserve the core text, update all internal links to new site URLs.

- Add CTA blocks (demo request) at natural break points. Add 'Related reading' section at bottom.

- Preserve original publish dates for SEO. Update meta descriptions.

- Verify URL slugs match old site for SEO continuity. Set up 301 redirects where slugs differ.

✓ Deliverables: 5 blog posts published in WordPress

Step 3.2: Migrate Tier 2 blog posts  →  Owner: Content

- ~15 posts covering maintenance strategy, pump monitoring, and water industry:

  - CBM: 5-step guide (7.5K)

  - CBM: pilot to scaling — 4-part series (27K total)

  - 10 proven maintenance strategies (13.7K)

  - Quick-start guide to PdM 4.0 (15K)

  - Remote CM for submersible pumps (16K)

  - 4 ways to cut pump energy costs (11.7K)

  - Storm overflow series — 3 parts (31K total)

  - Smarter sewers — 2 parts (19.4K total)

  - Path to Net Zero in water industry (19K)

  - Airlock in water pumps (8.1K)

  - Sewage pump overflow causes (7.5K)

  - Expert interview: DJW on CBM in water (11.2K)

  - 5 tips for electric motor reliability (6.4K)

  - Business case for PdM in manufacturing (6.9K)

- Same process as Tier 1: strip markup, update links, add CTAs.

- These can be migrated faster — they need less editorial review.

✓ Deliverables: ~15 blog posts published

Step 3.3: Merge knowledge base articles  →  Owner: Content

- Several KB articles overlap with new-site pages. Handle overlaps:

- Merge decisions:

  - How SAM4 detects pump faults (19K) → overlaps with how-it-works. Keep as blog, cross-link.

  - SAM4 pump blockage detection explained (7.5K) → merge key content into what-we-monitor.html. Redirect.

  - SAM4 real-time pump curve (11.4K) → merge into SAM4 platform page. Redirect.

  - SAM4 belt conveyor failures (4.9K) → merge into what-we-monitor.html. Redirect.

  - CM: 5 technologies to prevent failures (11.8K) → merge with the 5-technologies guide blog post.

- Archive: SAM4 PdM features, ERGO projects, Achieving resilience — these are dated product marketing.

✓ Deliverables: Merged content updated on target pages. Redirects configured.

Step 3.4: Archive thin/dated blog content  →  Owner: Content

- These posts are too thin or dated to migrate. Set up redirects only:

  - Vibration analysis for CM (2.5K) → redirect to ESA vs Vibration page

  - Oil analysis for CM (3K) → redirect to 5-technologies guide

  - Thermal analysis in CM (2.7K) → redirect to 5-technologies guide

  - Acoustic emission analysis (3.5K) → redirect to 5-technologies guide

  - CM in wind turbines (4.5K) → redirect to homepage or archive

  - Humans and machines: better together (3K) → redirect to about page

- Don't delete the old posts until redirects are verified working.

✓ Deliverables: Redirects configured for ~6 archived posts

Phase 4   News, Legal, FAQs, Cleanup

Duration: 1 week

Final sweep: migrate partnership announcements that carry backlink value, move legal pages verbatim, consolidate FAQs, and handle remaining items.

Step 4.1: Migrate high-value news/PR  →  Owner: Content

- ~15 news posts worth migrating (partnership and deal announcements):

  - Yorkshire Water £10M contract

  - ABB launches drives with ESA

  - Siemens enhances NXpower with Samotics

  - Southern Water £7M deal

  - Thames Water selects Samotics

  - Anglian Water 5-year deal

  - South East Water selects Samotics

  - United Utilities trials Samotics

  - Northern Ireland Water expands

  - thyssenkrupp selects Samotics

  - EIB €20M financing

  - Yorkshire Water + Samotics win award

  - Schneider Electric partnership

  - Eviden joint APM solution

  - London Stansted selects Samotics

- Light-touch migration: strip Elementor, fit into blog template, categorise as 'News'.

- These carry backlink equity. Preserve URLs where possible.

✓ Deliverables: ~15 news posts published

Step 4.2: Archive remaining news  →  Owner: Content

- ~15 news posts are dated (product launches superseded, old funding rounds, rebrands).

- Don't migrate these. Set up 301 redirects to the news archive page or homepage.

- Preserve in WordPress as drafts for historical reference.

✓ Deliverables: Redirects configured

Step 4.3: Migrate legal pages verbatim  →  Owner: Legal + Developer

- Privacy and cookie policy → copy text verbatim. Do not edit. Apply new site styling.

- Terms of usage → copy text verbatim. Do not edit. Apply new site styling.

- Verify: company name, registered address, chamber of commerce number, VAT number all current.

- Ensure cookie consent mechanism works with new site banner.

- Add both pages to footer navigation.

✓ Deliverables: privacy-policy.html and terms.html published · Footer updated

Step 4.4: Consolidate FAQs  →  Owner: Content

- The old site has 54 individual FAQ entries. Most overlap with content already on new-site pages.

- Action:

  - Audit all 54 FAQs against content on SAM4, how-it-works, how-it-installs, ESA, and security pages.

  - Any FAQ already answered on a page → no migration needed.

  - Remaining FAQs → group into sections: Technology, Installation, Dashboard, Security, Commercial.

  - Build a /faq page on the new site with collapsible sections.

  - Alternatively, embed FAQ sections at the bottom of relevant pages (better for SEO).

✓ Deliverables: FAQ audit spreadsheet · FAQ page or embedded sections published

Step 4.5: Handle events and webinars  →  Owner: Marketing

- 5 upcoming 2026 events: Global Water Summit, Maintec, SPE Europe, Utility Week Live, World Water-Tech.

- Migrate these to the blog or a dedicated /events section if events are a regular content type.

- 6 webinar pages: archive unless recordings are still generating leads. Redirect to blog.

✓ Deliverables: Event pages published or redirected

Step 4.6: Pricing page decision  →  Owner: Marketing + Sales

- The old site has a pricing page (5.5K chars). Needs a decision:

- Option A: Rebuild with current pricing model. Make it a conversion page.

- Option B: Remove public pricing and redirect to contact/demo flow.

- This is a business decision, not a content decision. Involve sales.

✓ Deliverables: Pricing page published or redirect configured

Step 4.7: Merge feature pages and product items  →  Owner: Content + Developer

- Old site has several feature-level pages and product items that need folding into the new site:

  - Sewage pump blockage detection (140K) → extract key content into water/wastewater pages + what-we-monitor

  - Electric submersible pumps (8.4K) → fold into oil-gas page + what-we-monitor

  - AMP8 (10K) → fold into water page if AMP8 still relevant to 2025–2030 cycle

  - 6 product entries (pump blockage, predictive alerts, asset reliability, asset map, Archimedes, reactor coolant) → ensure all covered by SAM4 page and what-we-monitor page

- Set up redirects from old URLs to the pages that absorbed the content.

✓ Deliverables: Content merged. Redirects configured.

Phase 5   Post-Migration Verification

Duration: 3–5 days

Don't skip this. Migration failures are invisible until a prospect hits a 404 or Google drops a page from the index.

Step 5.1: Test all redirects  →  Owner: Developer

- Crawl the full redirect map. Verify every old URL returns a 301 to the correct new page.

- Check for redirect chains (old URL → intermediate URL → final URL). Eliminate chains.

- Check for redirect loops. These will crash the page.

- Use Screaming Frog or a similar crawler to automate this.

✓ Deliverables: Redirect audit report — 0 broken, 0 chains, 0 loops

Step 5.2: Submit updated sitemap to Google  →  Owner: Developer

- Generate a new XML sitemap from the new site.

- Submit to Google Search Console. Request re-indexing of key pages.

- Monitor 'Coverage' report in Search Console for the next 2 weeks. Watch for 'Excluded' URLs.

✓ Deliverables: Sitemap submitted. Monitoring configured.

Step 5.3: Compare traffic after 2 weeks  →  Owner: Marketing

- Compare organic traffic against the analytics baseline from Phase 0.

- Check: are the top 50 organic pages still receiving traffic?

- Check: have any high-traffic old URLs dropped out of the index?

- If traffic drops on specific pages, investigate: redirect issue, content issue, or index issue?

✓ Deliverables: 2-week traffic comparison report

Step 5.4: Fix 'no downtime' claims  →  Owner: Content

- Flagged in prior sessions: incorrect 'no downtime' claims exist on several pages.

- Pages to fix:

  - how-it-works.html — review and correct any absolute claims

  - how-it-installs.html — hero + installation item claim no downtime

  - header.html — navigation dropdown

  - case-study.html template — check template text

- Replace with accurate language: 'installs without process interruption' or similar.

✓ Deliverables: All 'no downtime' claims corrected

Step 5.5: Update internal links across all new pages  →  Owner: Developer

- With all content now migrated, do a final sweep of internal links across every new-site page.

- Check: do industry pages link to their case studies? Do case studies link back to industry pages?

- Check: do blog posts link to new-site pages (not old URLs)?

- Check: does the footer include legal pages, FAQ, blog?

- Check: does the header navigation reflect the full site structure?

✓ Deliverables: Internal link audit — all links verified

# Appendix: What Not to Migrate

For clarity, here is everything from the old site that should not be migrated as a page. These items get a redirect or nothing.

Internal assets

Messaging house canvas, benefits canvas, SAM4 feature levels canvas, messaging foundation — internal marketing documents, not public pages.

Staging/test pages

New use case page 2025, ABB X Demo, Accenture X Demo — draft or empty pages.

Superseded product news

SAM4 2.0 launch, energy analytics launch, MV support, edge analytics, pump curve feature, Archimedes screw, asset map, new incident page — all product updates that are now baseline features. No ongoing value.

Dated corporate news

Series A announcement, rebrand, CEO message, Jeroen van der Veer advisory appointment — historical items with no current conversion value.

Thin technology posts

Vibration analysis (2.5K), oil analysis (3K), thermal analysis (2.7K), acoustic emission (3.5K) — too thin to stand alone. Content covered by ESA vs Vibration page and the 5-technologies guide.

Campaign landing pages

5 landing pages built for paid campaigns. Archive unless campaigns are still running.

Non-English webinars

Italian, Portuguese, Spanish variants of the same webinar. Archive unless there's a regional marketing plan.

Tour pages

Interactive product tour pages — likely use an external tool. Redirect to demo/contact.

Empty post-type entries

4 use-case entries and 6 product entries with 0 chars of content. These are taxonomy items, not pages.